## Ark2
Lofthus frukt og saft
ALSOL
André Lekve |  | Project start 27.01 - end 28.02 |  | January |  |  |  |  | February
|  |  |  | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
ID | Assignment | Assigned workers | Estimated time | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Making website | Everyone | 25 days | bar: Week 5 M to Week 5 F; Week 6 M to Week 6 F; Week 7 M to Week 7 F; Week 8 M to Week 8 F; Week 9 M to Week 9 F
2 | Meeting customer (farmer) | André | 2 days | bar: Week 5 M to Week 5 T; Week 6 F; Week 7 F
3 | Taking pictures for site | Ingeborg | 2 days | bar: Week 5 M to Week 5 T
4 | Design (colour, layout etc.) | Ingeborg + Daniel | 8 - 10 days | bar: Week 5 W to Week 5 F; Week 6 M to Week 6 F
5 | Translate language on website | Gjermund | 10 days | bar: Week 6 M to Week 6 F; Week 7 M to Week 7 F
6 | Front-end development | Vidar + André | 10 - 12 days | bar: Week 7 M to Week 7 F; Week 8 M to Week 8 F; Week 9 M to Week 9 T
7 | Quality Control | Gjermund + André + Vidar | 2 days | bar: Week 9 W to Week 9 T
8 | Presentation & delivery (28.02.20) | André + Ingeborg | 1 day | bar: Week 9 F